## Sheet1
Stand up meeting date: 24/ 04/ 2024
Team's name | A3-OOP-Airline-Management-System
Member's name | What did they do yesterday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Senghak Chhun | create UML Class Employees such as Employee, pilot, attendant, chef, co-pilot, | 7h 15m | 8h | 1. create UML Class Employees such as Employee, pilot, attendant, chef, co-pilot. 2. Research about Book Reference Number. | 4 h
Khlorp Veak | 1. Note stand up meeting. 2. Create UML class Adress, Person, Genger, Baggage | 8h | 8h | 1. Note stand up meeting. 2. Update UML class such as Airline, Baggage, Ticket, Booking, Airport, Aeroplane | 4h
Moeun Chandy | 1. Today we are going to Research about Ticket vs Booking 2. create UML class Ariport, Aeroplane, Flight, Airline, . | 8h | 7h | 1. Research about employee in airline 2. create UML class cabinCrew, operationAgent. | 4h
Stand up meeting date: 25/ 04/ 2024
Team's name | A3-OOP-Airline-Management-System
Member's name | What did they do Thursday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Senghak Chhun | 1. create UML Class Employees such as Employee, pilot, attendant, chef, co-pilot. 2. Research about Book Reference Number. | 4h | 3:50h | 1. start code about employee class, Passenger, air_traffic, attendants, chef, co_pliot, manager, operations, pliot. | 4h
Khlorp Veak | 1. Note stand up meeting. 2. Update UML class such as Airline, Baggage, Ticket, Booking, Airport, Aeroplane | 4h | 4h | 1. start code about Airline, booking, mael, and tast code in main, airport for Flights. 2.Note stand up meeting. | 4h
Moeun Chandy | 1. Research about employee in airline 2. create UML class cabinCrew, operationAgent. | 4h | 3:30h | 1. start code about Person in the Airport, gender in the Aeroplane, ticket of Aeroplane | 4h
Stand up meeting date: 29/ 04/ 2024
Team's name | A3-OOP-Airline-Management-System
Member's name | What did they do thursday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Senghak Chhun | 1. start code about employee class, Passenger, air_traffic, attendants, chef, co_pliot, manager, operations, pliot. | 4h | 4h | 1. check sine roler relationship | 4h
Khlorp Veak | 1. start code about Airline, booking, mael, and tast code in main, airport for Flights. 2.Note stand up meeting. | 4h | 4:15h | 1. Note stand up meeting. 2. edit MUL for relationstip its. | 4h
Moeun Chandy | 1. start code about Person in the Airport, gender in the Aeroplane, ticket of Aeroplane | 4h | 4:20h | 1. she is reseach of code shear 2. she is reseach of flieght namber | 4h
Stand up meeting date: 30/ 04/ 2024
Team's name | A3-OOP-Airline-Management-System
Member's name | What did they do Monday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Senghak Chhun | 1. check sine roler relationship | 4h | 4h | 1. Edit code on booking, Ticket, Employee. 2. Create add route on trips. 3. Taster on code and check code. | 4h
Khlorp Veak | 1. Note stand up meeting. 2. edit MUL for relationstip its | 4h | 4h | 1. Edit UML of relationship on booking, Ticket, Employee, flight, Aeroplane. 2. Create rout of UML. 3. Note stand up meeting. | 4h
Moeun Chandy | 1. she is reseach of code shear 2. she is reseach of flieght namber | 4h | 4h | 1. Researcher on rout and create add bagage. 2. Edit on Airline, Meal, Person. | 4h
Stand up meeting date: 01/ 05/ 2024
Team's name | A3-OOP-Airline-Management-System
Member's name | What did they do Tuesday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Senghak Chhun | 1. Edit code on booking, Ticket, Employee. 2. Create add route on trips. 3. Taster on code and check code. | 4h | 3h | 1. As an airline chef, I need to know, for a given flight, how many of each meal type I need to prepare | 4h
Khlorp Veak | 1. Edit UML of relationship on booking, Ticket, Employee, flight, Aeroplane. 2. Create rout of UML. 3. Note stand up meeting. | 4h | 4h | 1. Note stand up meeting 2. As an airline manager, I want to find out how much salary I pay all my employees. | 4h
Moeun Chandy | 1. Researcher on rout and create add bagage. 2. Edit on Airline, Meal, Person. | 4h | 3:30h | 1. Test code and create add new. 2. As a passenger, I want to know which gate my plane is waiting at | 4h
Stand up meeting date: 02/ 05/ 2024
Team's name | A3-OOP-Airline-Management-System
Member's name | What did they do Wednesday? |  |  | What you will do today?
| List down the task | Estimate time to finish | Actual finish time | List down the task | Estimate time to finish
Senghak Chhun | 1. As an airline chef, I need to know, for a given flight, how many of each meal type I need to prepare. | 4h | 4h | 1. Creat add add type meal in the flight. | 4h
Khlorp Veak | 1. Note stand up meeting 2. As an airline manager, I want to find out how much salary I pay all my employees. | 4h | 4h | 1. Note stand up meeting. 2. Tast code. | 4h
Moeun Chandy | 1. Test code and create add new. 2. As a passenger, I want to know which gate my plane is waiting at | 4h | 4h | 1. As a passenger, I want to know which gate my plane is waiting. | 4h